## Defect Tracking Sheet
DEFECT TRACKING SHEET - Student Registration System
Prepared by: Ruknuddin Asrari ¦ Software Quality Engineer ¦ IT Software Development ¦ ruknuddin.asrari@thecareerinsights.com ¦ March 2026
Bug ID | Module | Title | Description | Severity | Priority | Status | Assigned To | Environment | Date Raised | Date Fixed | Comments
BUG-001 | Login | User Remains Logged In After Logout | Session not destroyed on logout; Back button restores authenticated pages | Critical | High | Open | Ruknuddin Asrari | Chrome 120, Win11 | 26-Mar-2026 |  | Blocks release – investigate session destroy mechanism
BUG-002 | Student Signup | Duplicate Email Registration Succeeds | No server-side duplicate email check; second account created | Critical | High | Open | Ruknuddin Asrari | Firefox 121, Win11 | 26-Mar-2026 |  | Add unique constraint check on email field
BUG-003 | Login | No Account Lockout After Failed Logins | Unlimited login attempts allowed; no lockout or CAPTCHA triggered | High | High | Open | Ruknuddin Asrari | Chrome 120, Win11 | 26-Mar-2026 |  | Implement 5-attempt lockout with 15-min timeout
BUG-004 | Student Signup | Weak Passwords Accepted | Password '123456' accepted; no complexity validation on server | High | High | Open | Ruknuddin Asrari | Chrome 120, Win11 | 26-Mar-2026 |  | Add server-side regex validation for password strength
BUG-005 | Course Enrollment | Duplicate Enrollment Allowed | Student can enroll in same course multiple times; records duplicated | High | High | Open | Ruknuddin Asrari | Firefox 121, Win11 | 26-Mar-2026 |  | Check enrollment status before processing new request
BUG-006 | Profile Update | Profile Changes Not Saved | Save button does not persist data; no error or success message shown | High | High | In Progress | Ruknuddin Asrari | Chrome 120, macOS | 26-Mar-2026 |  | Dev investigating DB transaction issue – ETA 28-Mar
BUG-007 | Admin Dashboard | Student Access to Admin Dashboard | Student can access /admin/dashboard via direct URL; no RBAC check | Critical | High | Open | Ruknuddin Asrari | Chrome 120, Win11 | 26-Mar-2026 |  | Add server-side role check on all admin routes
BUG-008 | Course Enrollment | Full Course Enrollment via API Bypass | UI disables button but API allows enrollment in 0-seat courses | High | High | Open | Ruknuddin Asrari | Postman, Chrome 120 | 26-Mar-2026 |  | Enforce capacity check in API endpoint server-side
BUG-009 | Student Signup | 500-Char Input Accepted in Name Fields | No max-length server validation; long strings stored in DB | Medium | Medium | New | Ruknuddin Asrari | Firefox 121, Win11 | 26-Mar-2026 |  | Add maxlength=100 server-side validation to all text fields
BUG-010 | Admin Dashboard | Enrollment Count Not Real-Time | Count stale until admin manually refreshes; no auto-update mechanism | Medium | Medium | New | Ruknuddin Asrari | Chrome 120, Win11 | 26-Mar-2026 |  | Implement auto-refresh or WebSocket push for report counts

## Summary Dashboard
DEFECT SUMMARY DASHBOARD
Student Registration System ¦ Ruknuddin Asrari ¦ March 2026
BY MODULE
Module | Defect Count | Severity Breakdown
Login | 3 | Critical x1, High x2
Student Signup | 3 | Critical x1, High x2
Course Enrollment | 2 | High x2
Profile Update | 1 | High x1
Admin Dashboard | 2 | Critical x1, Medium x1
TOTAL | 0 | Critical x3, High x6, Medium x2
BY STATUS
Status | Count | Notes
Open | 7 | Requires immediate developer attention
In Progress | 1 | BUG-006 – Profile update DB fix in progress
New | 2 | BUG-009, BUG-010 – Pending triage
Fixed | 0 | No defects fixed yet
Closed | 0 | No defects closed yet
TOTAL | 10
BY SEVERITY
Severity | Count | % of Total
Critical | 3 | 27.2727
High | 6 | 54.5455
Medium | 2 | 18.1818
Low | 0 | 0
TOTAL | 11

## Bug Lifecycle Reference
BUG LIFECYCLE QUICK REFERENCE
Prepared by: Ruknuddin Asrari ¦ Software Quality Engineer ¦ March 2026
Status | Owner | When | Transitions To | Background Color
New | Tester | Defect just discovered and logged for the first time | Open / Rejected | D6E4F7
Open | QA Lead | Reviewed, accepted, assigned to developer | In Progress / Rejected / Deferred | FFEDD5
In Progress | Developer | Developer actively working on fix | Fixed | FEF9C3
Fixed | Developer | Fix implemented and deployed to QA | Retest | DCFCE7
Retest | Tester | Tester verifying the fix | Closed / Reopened | EDE9FE
Closed | Tester | Fix verified and confirmed resolved | (terminal state) | DCFCE7
Reopened | Tester | Fix failed; defect re-raised | In Progress | FEE2E2
Rejected | QA Lead | Not valid, duplicate, or not reproducible | (terminal state) | F3F4F6
Deferred | PM / QA Lead | Fix postponed to future release | (reviewed each sprint) | FEF9C3